## WEB Development
Stand up meeting Minute Book for Web development
TCY= Tasks completed yesterday
PTC= Planned task for completion today
34 TOP | 4TCY | 2PTC |  | What did I work on yesterday? | What am I working on today? | What issues are blocking me?
|  |  | 2023-07-12 | [6 empty] | TCY = Tasks completed yesterday
PTC= Planned task for completion today
|  |  | Aqsa | created jira acconut (100%)
|  |  |  | created Domain (halee financials) (100%) | Created jira account for fatma (100%) | Max- site issue with domain overlapping with jungle safari |  |  |  | 34 TOP, 4TCY, 2PTC
|  |  |  | Assigned emails (5 emails yesterday made for Haleefinancials) | Created 5 more today (total of 10 emails) (100%)
|  |  |  | Assigned project to max, unzila, asqa and haseeb | assigned project to fatma (100%) |  |  |  |  | The abbreviations were updated to avoid any confusion, please provide me feedback.
Install SSF certificate on haleefinanancials
|  |  | Fatima | Created jira account | Running a google analysis on remaining 6 websites | Max-websites are not listed on the C panel tool kit
|  |  |  | created google analyst account (100%) |  | Max-need access for admin for the panel
Installed free apps on jira (100%)
google analysis on two websites (100%)
[5 empty] | install world press on halee financials website (completed 100%) | Max- need login id for websites (Raha is one of website
|  |  | Unzila | created jira account
created 1 domain with aqsa
created emails
2023-07-14
|  |  | Unzila | i install the app on jira(100%) | improving the affordablejunglesafari.com website | max-providing username and password of http://affordablejunglesafari.com/wp-admin
|  |  |  | start the Associate Android Developer Certification program(20%) | generate the project plan for affordablejunglesafari website
|  |  |  | search the method to develop app for website(50%) | continue certification (30-40%)
write down the task for improving the website(50%)
search the name for web development company(100%)
|  |  | aqsa | Created an email for myer (100%) | Integrate ecommerce to order bookkeeping services | dont have the access to the backend of bookkeepingworldwide.com
|  |  |  | Created the jira account(100%) | Comapre the other top sites with bookkeepingworldwide.com
Created an email for tayabba (100%)
Created jira account for tayyaba for haleefinancials(100%)
recreated a new domain for haleefiananancials (100%)
Installed SSL for haleefinancials (100%)
attached the hosting to the name servers(100%)
set all the emails of haleefinancials again(100%)
Assigned project to myer(100%)
Assigned tasks to myself on jira
|  |  | Fatima | created jira task
|  |  |  | install wordpress webside and run Google analytics on it | have to install remaining website's | max_dont have ionos access
have to run google analytics on websites
2023-07-15
|  |  | unzila | create the multi borad | Setup auto Schedule backup for all Raha websites (Wordpress and Cloudflare)(50%)
|  |  |  | start the Associate Android Developer Certification program(30%) | start the Associate Android Developer Certification program(40%)
search the method to develop app for website(60%)
write down the task for improving the website(60%)
|  |  | Aqsa | Created Fiverr account | Applied for certification
|  |  |  | Explored fiverr | Selected the topic for ML project
|  |  |  | Created the list for ecommerce packages for bookkeepingworldwide | Searched datasets
Research on Ecommerce sites
|  |  | fatima | configure jira | go though google work space specialities and cost | max-don't have access to ionos accounts
|  |  |  | Added labels and categories for projects | gave to run google anaytics
go through different google work spaces and their packages
created upwork account
|  |  | tayyaba | I install jira apps like: Todolist, checklist, event clandar, Team Reports | explore w4u infotech
I install SEO Plugins in Eviction
All in One SEO
gone through w4v infotech
explore jira
|  |  | Myer | Work on compare eviction website | Redo Raha Website
Research on SEO
|  |  | Haseeb | Investigate to about the Raha properties | Setting up Github for backups
2023-07-17
|  |  | Fatima | created a spread sheet for ionos username and passwords(30%) | have to add more ionos login credintials | max-all of ionos accounts credentails are not in raha propertes gmail account
|  |  |  | created more labels for task and issues | Have to start reading 7 habbits
|  |  |  | created categories for projects | learn how to use ftp client zilla
|  |  |  | Go to how to backup system(40%) | Identify the Plaintiff's with eviction cases
install ftp client zilla(100%)
go through procedure of migrating mails from webmail to google(100%)
|  |  | Aqsa | research on the backup (70%) | learn 4 disciplines of execution(30%)
|  |  |  | Investigate the backup for rahaproperties(80%) | Robin sharma's 50 rules | max : cannot access the book
[5 empty] | setup the haleefinanancials with correct spelling domain(20%) | cannot get the credential
|  |  | tayyaba | Install ftp client.
|  |  |  | Install apps in jira: API key Manager for Jira, Day.io, Database Exporter, Better Excel | setup autoposter for houston(10%)
|  |  |  | Set SEO's for eviction | Read 7 habits(10%) | Max- Donot have W4U infotech Server Email and password
|  |  |  | Research on autoposter configuration and setup |  | Aqsa-after the domain site with correct spelling is completely setup
|  |  | Myer | Research SEO | Work on Raha Website | Wont let me log in
unzila
|  |  | Haseeb | Redsearch on the backup and trash | Setting up Github for backups
Tried to restore the Raha properties
|  |  | Hamna | log in to accounts | watching tutorials to explore jira and cpanel to understand my tasks | had a few questions regarding my tasks
|  |  |  | learn how to create jira | Created my jira account
access google drive
2023-07-18
|  |  | fatima | made a list of apartment communities with most number of eviction cases(100%) | read 7 habbits(5 pages) | no blocks
|  |  |  | install compareeviction on wordpress | learn about ftp client zilla
create backup for compareeviction
read 7 habbits of higly effective people(4 pages)
restore compareeviction(100%)
|  |  | Tayaba | create backups for junglesafari | Write script to Search online and find out the Apartment Complexes data
|  |  |  | install seo plugins in junglesafari(40%) | continue 7 habbits
restore junglesafari(90%)
start 7 habbits(8%)
start working on auto poster on houston.craigslist(10%)
Create task for hamna
Created Dashboard for jira with name of Project Health(100%)
|  |  | Aqsa | learned about the four disciplines of execution(60%) | Robin sharma's 50 rules(20%)
|  |  |  | research on SPF record (80%) | Web Development company names suggestions(100%)
research on SPF record (100%)
|  |  | Haseeb | Setup Github for backups | Work on Raha website | Dont have access to Raha admin panel
|  |  |  | Gave Hamna the orientation about our work and Jira | Will create a spreadsheet for the daily standup meeting hosts
Put buttons like start date,proirity etc in Jira
|  |  | Hamna | Created an account on Jira
Logins to cpanel, web mail, and access to google drive
Unzila
|  |  | Myer | Read 50 rules of work | redo the raha website | I need wordpress login it changed
2023-07-19
|  |  | Tayyaba | create auto poster for craigslist (30%)
|  |  |  | watch vedios on how to add payment methode on website | continue work on auto posters | evictionrighnow password are not listed on sheet
|  |  | fatima | read 7 habbits (3 pages) | look for dismissed evition cases (100%)
install plugins for campare eviction
learn how to do seo(30%)
|  |  | unzila | Setup autoschedule backup for all Raha websites(wordpress and cloudflare)2 websites | working on https://affordablejunglesafari.com/ (adding content+ images) | max- given me google drive
|  |  |  | Create Multi-Project Jira board | learning The 4 Disciplines of Execution
|  |  |  | start the Associate Android Developer Certification program(45%) | Setup auto Schedule backup for all Raha websites (Wordpress and Cloudflare)
|  |  |  | search the method to develop app for website(70%) | reading (master reader technique book)(no# 1)
|  |  |  | write down the task for improving the website(70%) | Reading this book and Practice these habits
|  |  | aqsa | learned about the four disciplines of execution(70%) | Robin sharma's 50 rules(30%)
|  |  |  | me and haseeb worked to reset the passwords for domains(10%) | secured the domains credentials google sheet with scripting(100%)
myer
|  |  | hamna | started reading 7 habits of highly effective people | have to create a google form to collect eviction tenant information from clients | couldnt find the attached screenshots to update my dashboard
|  |  |  | Installed filezilla (100%) | Figure out the cost and time required on How to Migrate our Custom Domain’s Email to Google | couldn't access the google sheet
set up free apps and dashboard task (40%)
2023-07-20
|  |  | Fatima | go through first disciplines of exection(40%) | do google analitics for campareeviction
|  |  | Unzila | working on https://affordablejunglesafari.com/ (adding content+ images) | working on https://affordablejunglesafari.com/ (adding content+ images)
|  |  |  | learning The 4 Disciplines of Execution(2 rule)(40%) | learning The 4 Disciplines of Execution(2 rule)(40%)
|  |  |  | Setup auto Schedule backup for all Raha websites (Wordpress and Cloudflare)(40%) | Setup auto Schedule backup for all Raha websites (Wordpress and Cloudflare)
|  |  |  | reading (master reader technique book)(no# 1) few pages | reading (master reader technique book)(no# 1) few pages
|  |  |  | Reading this book and Practice these habits(30%) | Reading this book and Practice these habits
|  |  | Aqsa | me and haseeb worked on haleefinancials login credentials for ionos(100%) | created the current domain with right spelling of haleefinancials (100%)
|  |  |  | learnt Robin Sharma’s 50 New Rules of Work( 20 rules) | Domain pointed to server (100%)
|  |  |  | implement the 1st disipline out of the 4 Disciplines of Execution | Added addon domain (100%)
Installed wordpress (100%)
SPF record added in Domain DNS ( haleefinancials)
|  |  | Hamna | read a page of 7 habits of highly effective people | read a page of 7 habits of highly effective people | no blocks
|  |  |  | learnt about the first discipline of execution | learn about the second discipline of execution
|  |  |  | Setup Jira free apps and dashboard task (100%) | complete task How to Migrate Custom Domain’s Email to Google
Create a google form to collect eviction tenant information from clients (100%)
|  |  | Haseeb | me and aqsa worked to recovered the credentials for current domain (haleefinancials) | Start the book 7 habits
|  |  |  | Watch youtube videos about the wordpress | Doing ionos credentials work
Work on credentials for websites
|  |  | Tayyaba | create auto posters
create dumy website for adding payment methods
read 7 habits
|  |  | myer | raha website | raha website
|  |  |  | read 50 rules of work | read 7 habits of highly effective people
2023-07-21
|  |  | Tayyaba | read 7 habits
read 50 rules
download remote desktop
|  |  | Fatima | list the dismissed evition cases in july 2023 | download chrome remote desktop
|  |  | Humna | installed Chrome Remote Desktop | read a page of 7 habits of highly effective people | no blocks
|  |  |  | read a page of 7 habits of highly effective people | learnt about the third discipline of execution
|  |  |  | learnt about the second discipline of execution | watch tutorials from the rahaweb gmail drive
completed task of Migrating Custom Domain’s Email to Google
|  |  | Aqsa | Implement the 1st disipline out of the 4 Disciplines of Execution | worked on haleefinanancials(wrong spelling one)
|  |  |  | learnt Robin Sharma’s 50 New Rules of Work( 25 rules) | intalled spf
addon domain
installed the chrome remote desktop (100%)
investigate the bookkeepingworldwide .com
|  |  | unzila | working on Affordabalejungle websites
|  |  |  | learnt Robin Sharma’s 50 New Rules of Work( 5 rules) | working on Affordabalejungle websites
|  |  |  | install remote google | learnt Robin Sharma’s 50 New Rules of Work( 10 rules)
|  |  |  | mater reader book( few more pages) | mater reader book( few more pages)
complete 2 task on jira
|  |  | Myer | Work on raha website | read one of the books
work on raha website
2023-07-22
|  |  | unzila | working on Affordabalejungle websites | working on Affordabalejungle websites
|  |  |  | learnt Robin Sharma’s 50 New Rules of Work( 10 rules) | learnt Robin Sharma’s 50 New Rules of Work( 20 rules)
|  |  |  | mater reader book( few more pages) | mater reader book( few more pages)
|  |  | Hamna | read a page of 7 habits of highly effective people | read a page of 7 habits of highly effective people | no block
|  |  |  | learnt about the third discipline of execution | learn about the 4th discipline of execution
|  |  |  | watch tutorials from the rahaweb gmail drive | master reader book
watch tutorials to do research on github & jira
|  |  | Myer | work on raha property
|  |  |  | read 7hohsp | work on raha property website | need tenant tracker
2023-07-24
|  |  | Aqsa | Implement the 2nd disipline out of the 4 Disciplines of Execution | working on recovery of domains credentials
taking google UX design course
|  |  | Myer | work on raha website | work on raha website
|  |  |  | read 7hohsp | read 7hohsp
2023-07-25
|  |  | aqsa | take google UX design course | Implement the 3rd disipline of Execution
|  |  |  | work on the credentials | installed FileZila
|  |  |  | learn master reading techniques(20%) | Learn about FileZila
working on domains credential sheet
Learn master reading skills(30%)
|  |  | unzila | reading book master reader | reading book master reader
|  |  |  | reading book 7 habit of highly effective people | reading book 7 habit of highly effective people
|  |  |  | working on afforablejungle website | working on afforablejungle website
push website on github
|  |  | Hamna | collecting everyones resumes | Reading 7 habits of highly effective people | no blocks
|  |  |  | Reading 7 habits of highly effective people | Think of company names
|  |  |  | learning jira | learn jira watch tutorials
work on my task of creating resumes
2023-07-26
|  |  | Max | Team - Update your jira tasks with estimated hours, start date and due date
Team - Have a 30mins mtg to pick on the company name today after daily standup
|  |  | Fatima | start google analytics for haleefinanancials
|  |  |  | install sitekit for haleefinanancials | learn how to do SEO
|  |  |  | Read 7 habits(4 pages) | READ 7 HABBITS
|  |  | Aqsa | Explore the wordpress | Implement the 4th disipline of Execution
|  |  |  | learn master reading techniques(5%) | Working on redirect the domains(haleefinancials+haleefinanancials)
|  |  |  | to do tasks (4) | take the google UX design course(15%)
in progress(15)
done(9)
|  |  | unzila | reading book master reader(30%) | reading book master reader
|  |  |  | reading book 7 habit of highly effective people(30%) | reading book 7 habit of highly effective people
|  |  |  | working on afforablejungle website | working on afforablejungle website
in progress tasks(2)
completed tasks(22)
|  |  | Hamna | Reading 7 habits of highly effective people | read 7 habits of highly effective people | 4 team members have shared their cv's 2 are left.
|  |  |  | think of company names task | work on communication skills
|  |  |  | learning jira watched 5 tutorials | learn jira and watch more tutorials in a sequence
|  |  |  | working on communication skills | complete task of Resumes(70%)
remaining tasks(6)-to do
in progress-4
completed tasks(11)
|  |  | Tayyaba | SEO's for haleefinancials | Add payement methods for evictionrightnow(100%)
Download remote chrome desktop
Read 7 habits
Set autoposters for craigslist
to do tasks-(1)
in progress(4)
completed( 9)
|  |  | Haseeb | Created Github accounts for the team(75%) | Creating Github accounts for the team
|  |  |  | Checking Log in credentials | Checking the remote setups
to do ( 8)
in progress( 1)
done(1)
|  |  | Myer | work on raha website | work on raha website
to do -13
in progress(1)
done(0)
27/7/2023
|  |  | Hamna | Reading 7 habits of highly effective people | Reading 7 habits of highly effective people | Have not yet recieved Resumes of 2 members yet | 6 | 4 | 0
|  |  |  | Working on my resume task | Working on my resume task
|  |  |  | Learning Jira watching tutorials | Learning Jira watching tutorials
|  |  |  | Thinking of company names | Finalize company name with team
work on my communication skills
|  |  | Aqsa | learn master reading techniques(45%) | updated my resume and upload on jira (100%)
|  |  |  | learnt Robin Sharma’s 50 New Rules of Work (30 rules) | redirect the domain of haleefinanancial with correct one |  | 4 | 14 | 10
|  |  |  | Worked on the webmails which were not working (100%) | Explained the time sheet to the team members
check the available company's names
|  |  | unzila | reading book master reader(30%) | Thinking of company names
|  |  |  | reading book 7 habit of highly effective people(30%) | reading master reader (35%)
|  |  |  | working on afforablejungle website | habit book (35%)
|  |  |  | resume | working on affordablejungle website
in progress tasks(2)
completed tasks(23)
|  |  | Tayyaba | Suggest company name | Complete payment method and checkout page
read 7 habits(40)
Set autoposters
creat stripe payment method for evictionrightnow(40%)
28/7/23
|  |  | Fatima | download chrome remote desktop(100%) | read 2nd discipline of execution |  | 1 | 2 | 3
|  |  |  | read 7 habbits( 4 pages) | set upwork account(100%) | no blocks
create account on upwork (50%)
complete the first discipline of execution
think names for campany
|  |  | Tayaba | create payment method for evictionrightnow(80%) | complete method and integrate with evictionrightnow
|  |  |  | 7 habbits ( 3rd habbit) | complete autopoters for website(100%)
autoposters
|  |  | Aqsa | check the company's name availability | selected the top 3 as per team's vote (100%)
|  |  |  | Seclected the available names (100%) | research on the haleefinancial domain error(50%) |  | 4 | 9 | 18
|  |  |  | collect the 3 names from each team member | shared my required resume info with hamna(100%)
|  |  |  | learnt Robin Sharma’s 50 New Rules of Work (35 rules) | enter my working hours in time sheet
Explain the webdev time sheet to the remaining members
|  |  | Haseeb | Figured out the names for out company(With Aqsa) | Figuring out hte names for our company (With Aqsa)
Backing Up raha website
|  |  | hamna | reading 7 habits of highly effective people | reading 7 habits of highly effective people | waiting for information from team members
|  |  |  | completing task of resume | completing task of resume
|  |  |  | Think of company names with team | Learning jira watching tutorials
|  |  |  | Learning jira watching tutorials | work on communication skills
|  |  | Unzila | reading book master reader(35%) | Thinking of company names
|  |  |  | reading book 7 habit of highly effective people(35%) | reading master reader (40%)
|  |  |  | working on afforablejungle website | habit book (40%)
|  |  |  | learning about app developement | working on affordablejungle website
|  |  |  | in progress tasks(2) | push the Raha properties website code on gitbut
|  |  |  | completed tasks(23) | push the affordablejungle website on gitbut
|  |  | Myer | finish raha website (90%) | finish raha website (100%)
read book
start SEO project
29/7/23
|  |  | Aqsa | Robin Sharma’s 50 New Rules of Work (40 rules) | think of new names of company
|  |  |  | Research on different bookkeeping websites (45%) | check the availability of company's name
|  |  |  | Continue the certification coure (20%) | Register the company
|  |  | Unzila | adding estimate in my jira task
Updating my time Sheet (100%)
|  |  |  | reading book master reader(35%) | reading book master reader
|  |  |  | reading book 7 habit of highly effective people(35%) | reading book 7 habit of highly effective people
|  |  |  | working on afforablejungle website | working on afforablejungle website
|  |  | Fatima | go through evictionrightnow analytics | have to connect evictionrightnow to my google analytics account |  | 2 | 4 | 2
|  |  |  | explore its admin panel(70%) | go through evictionrightnow adminpanel(100%)
update timesheet(100%)
read 7 habbits (4 pages)
|  |  | Tayaba | making auto posters(40%) | work on autoposters(30%)
|  |  |  | work on payment method for evictionrightnow(70%) | work on payment methode (20%)
|  |  |  | read 7 habbits (10%) | read 7 habbits
|  |  |  | update timesheet(70%) | complete timesheet(100%)
|  |  | Hamna | Reading 7 habits of highly effective people | start reading master reader | Myer's resume is left
|  |  |  | worked on resume task(90%) | Reading 7 habits of highly effective people
complete resume task
Work on the new project for software company
31/7/2023
|  |  | Aqsa | worked on time sheet (99%) | start part1(Chapter strategies) of master reader book |  | 4 | 9 | 13
|  |  |  | watch videos regarding problems while working | installed plugins for haleefinanancials (100%)
|  |  |  | Continue the certification coure (22%) | added the required plugins
|  |  |  | Finalized the company's name and registered haleetech(100%) | work on haleefinanancials
created fiverr account(100%)
created upwork account(80%)
working on haleefinanancials(60%)
|  |  | Haseeb | Backed up Raha website | Putting new Haleetech emails on GitHub accounts(100%)
Updated the time sheet
|  |  | unzila | reading book master reader(100%) | working on afforablejungle website
|  |  |  | reading book 7 habit of highly effective people(100%) | working on heleetech wesbite
|  |  |  | working on afforablejungle website | updating my linkdin account info(100%)
|  |  |  | create a backup on Cpanel(100%) | create Fiverr and Upwork(50%)
Finalized the company's name and registered haleetech(100%)
in progress tasks(2)
completed tasks(23)
|  |  | Hamna | Created task for fiverr, upwork and LinkedIn. Assign to all. | Learning jira watching tutorials | no blocks
|  |  |  | Reading 7 habits of highly effective people | Reading 7 habits of highly effective people
|  |  |  | Completed task of Resume (100%) | Find small software websites for ideas and collaborate with unzila
|  |  |  | Learning jira watching tutorials | create my linkedin, fiverr and upwork account
myer
|  |  | Tayaba | Autoposter for houston website
Read 7 habits
determine which app is best for our database
write online script to findout apartment complexes
create fiver account
|  |  | Fatima | Setup a github
Read 7 habits
set LinkedIn account
wroking on data analysis
Create Fiver account
2023-01-08
|  |  | unzila | reading master reader (40%) | reading master reader (100%)
|  |  |  | updating my linkdin account info(100%) | working on affordablejungle demo website
|  |  |  | create Fiverr and Upwork(50%) | create Fiverr and Upwork(50%) | no block | 2 | 4 | 25
|  |  |  | push the Raha properties website code on gitbut (100) | search the content for halee tech start working on creating (50%)
push the affordablejungle website on gitbut
working on affordablejungle demo website
create logo for haleetech (100%)
searching the design and color
|  |  | Aqsa | start part1(Chapter strategies) of master reader book | start part1(Chapter strategies) of master reader book (40%) |  | 4 | 9 | 15
|  |  |  | Robin Sharma’s 50 New Rules of Work (40 rules) | Robin Sharma’s 50 New Rules of Work (45 rules)
|  |  |  | work on content for halee tech with hamna (15%) | Created my upwork account(100%)
|  |  |  | updated my linkedin account (100%) | Collect the content for haleefinancials and for haleetech (25%)
|  |  |  | work on haleefinanancials(60%) | Collect images for halee tech
[5 empty] | create FB account for halee tech | max : email
assign tasks to myself
|  |  | Fatima | Read Master Reader book(10%) |  |  | 2 | 4 | 2
|  |  |  | update Linkedin Account(60%) | update linked account | no blocks
|  |  |  | Created Upwork Account(100%) | set up fiver account(100%)
add hours estimation on jira task
|  |  | Tayyaba | Created LinkedIn Account(100%) | Complete ML program on extraction of eviction cases
Created Fiver and Upwork account(100%)
Created Tiktok accout for New Company(70%)
Read 7 habits(3 habits)
|  |  |  | Write a AI/ML program to extract eviction cases(40%) |  | no blocks | 4 | 5 | 3
|  |  | Hamna | Created my LinkedIn account(100%) | create my Upwork and Fiverr account | no blocks | 11 | 5 | 2
|  |  |  | Find ideas and templates for software company (100%) | Finalize the Website content front end with Aqsa and Unzila
|  |  |  | Collaborated with Aqsa and Unzila to decide the theme and logo | watch 2 more tutorials to learn jira
|  |  |  | Watched 2 tutorials to learn jira | Assign more tasks to the team acc to their skills for the new company
|  |  |  | Read the 1 habit of highly effective people (BE PROACTIVE) | Read the 2nd habit of highly effective people
assign tasks to myself
Assigned task to all team members to create their upwork, fiverr and linkedin account(100%)
2023-02-08
| 2 | 3 | tayyaba | Udated the Piechart orignal estimate
Updated LinkedIn Account(90%)
Create AI program to extract eviction Cases(90%)
Watch Tutorial on Database extraction(50%)
Read 7 habbits(60%)
|  |  | fatima | Read 7 habbits(40%)
Update Time sheeet(100%)
Update LinkedIn Account Profile(90%)
Perform Data Analytics for haleetech(20%)
|  |  | hamna | Read 2nd habit (Begin with the end in mind) | Create youtube channel for the company | no blocks
|  |  |  | Updating my upwork and Fiverr account | Learn about fiverr
|  |  |  | Assigned task to all team members to find projects on upwork | Read 3rd habit of highly effective people
|  |  |  | , fiverr and linkedln | Collect content of Website and Youtube channel
|  |  |  | watched 1 tutorial to learn jira | Watch 1 tutorial to learn jira and Github
| 1 | 2 | myer | Start SEO (long term project) | SEO for rahaproperties
|  |  |  | shared Resume (100%) | read the second chapter of 7hohsp
|  |  | haseeb |  | Create upwork and fiverr account
Creating linkedin account
| 3 | 2 | unzila | reading master reader (100%)
|  |  |  | working on affordablejungle demo website | working on affordablejungle demo website
|  |  |  | create Fiverr and Upwork(100%) | working on haleetech | no block
search the content for halee tech start working on creating (50%)
| 3 | 3 | Aqsa | create upwork and fiverr account(100%) | Robin sharma's 50 Rules
|  |  |  | take certification course (21%) | search content for haleetech
|  |  |  | learn 2 habits | work on haleefianancials
|  |  |  | assign jira tasks to myself | redirect the domain | no block
assign tasks to myself
start work on bookkeeping
2023-03-08
| 2 | 2 | unzila
|  |  |  | working on affordablejungle demo website | working on affordablejungle demo website
|  |  |  | working on haleetech | working on haleetech
working on fiverr account
creating upwork account
|  |  | hassab | working with fiverr account | creating a new domain on haleetech
|  |  |  | create a fiverr account | creating email of haleetech
install ssl on haleetech website
| 3 | 2 | aqsa | working on fiverr account | work on haleefianancials
|  |  |  | learn 3 habit | comparsion bookkeeping websites
|  |  |  | assign jira task my-self | start work on bookkeeping
|  |  |  | work on haleefianancials | pull the haleetech domain to shoaib server(100%)
|  |  |  | redirect the domain | install ssl on haleefinanel website
start work on bookkeeping

## Feedback
Encourage team members in giving facts, figures, % towards goal completion
Should be adopt the confluence templates?
Shout we setup up our story board on Confluence for each vertical companies?
Add responsible team member for clearing the block